LPR System Update to Council

- 10/28/2021 - System approved by Council via R-2022-005 for 27 cameras at 13 locations at a cost NTE of $344,400.

- Additional 2 cameras requested for Marvin Lane (privately funded).

- January 5, 2022 - PO issued

- January 6th - Site visit to confirm locations performed with contractor.

- February 4th - advised that VSS had ordered equipment.

- March 29th – advised by VSS that equipment and poles were received.

- April 5th - Advised that 11 of 14 locations received permits.  Additionally, two locations require Broward County approval for ROW placement and one was awaiting Davie approval.

- May 18th - 1st LPR location (Town Hall) installed.

- June 8th – County approved RLAs for placement of LPRs.

- July 14th – FPL Engineer indicated that all sites had been verified.

- August 9th – FPL is refusing (at staff level) to allow electrical subcontractor to tap into street light circuit.  This will require the use of transformers which will significantly increase project costs (approximately $10K).

Remaining Issues:

- SW 126 Avenue and Griffin Rd – need an additional RLA to place LPR in what we believe to be County ROW.

- Marvin Lane – FPL underground caused relocation of pole requiring directional boring from a pad mount transformer that will require funding (privately funded).

- SW 209 Avenue – FPL refusal to allow tapping street light circuit will require substantial reconfiguration to provide power to pole requiring additional funding.

- 6700 SW 172 Ave - FPL refusal to allow tapping street light circuit will require substantial reconfiguration to provide power to pole requiring additional funding.

Outlook:

- Ongoing meetings with project team to resolve issues – next meeting August 23rd.  May need to lobby FPL Government Liaison to assist.

- Project timeline – some poles will begin to be set in the next two weeks.  Project completion for all 14 locations and 29 cameras is mid to late October.